## Build Plan
Yap Fantasy - Build Plan to Kickoff
Set Status on each row. Milestones tab counts update automatically.
ID | Phase | Task | Start | Due | Days | Status | Depends On | Cut Order | Notes
1 | P0 Foundations | Enroll Apple Developer Program ($99/yr) | 2026-08-18 | 2026-08-18 | 1 | Not started |  | Blocker | Takes 24-48h. Nothing reaches a device until it clears.
2 | P0 Foundations | Subscribe balldontlie NFL GOAT ($39.99/mo); store key in Supabase secrets | 2026-08-18 | 2026-08-18 | 1 | Not started |  | Blocker | 600 req/min. Key lives in Edge Functions only.
3 | P0 Foundations | Scaffold Expo Router app (TypeScript, expo-router, reanimated, nativewind) | 2026-08-18 | 2026-08-19 | 2 | Not started |  | Blocker | Verify web AND iOS simulator both render on day one.
4 | P0 Foundations | Supabase project + CLI linked + migrations workflow | 2026-08-19 | 2026-08-19 | 1 | Not started | 2 | Blocker | Every schema change is a migration file. No dashboard clicks.
5 | P0 Foundations | Auth: Supabase email magic link | 2026-08-19 | 2026-08-20 | 2 | Not started | 3, 4 | Blocker | Magic link only = no Sign in with Apple needed. Google/X login would force it.
6 | P0 Foundations | App Store Connect app record + bundle ID + app icon | 2026-08-20 | 2026-08-20 | 1 | Not started | 1 | Blocker | Placeholder icon is fine, it just cannot be empty.
7 | P0 Foundations | First EAS dev build installed on your own iPhone | 2026-08-20 | 2026-08-21 | 2 | Not started | 3, 6 | Blocker | Signing/provisioning eats 2-3 days. Lose them now, not in September.
8 | P0 Foundations | Deploy web build to Vercel/Cloudflare + auto-deploy on push | 2026-08-21 | 2026-08-21 | 1 | Not started | 3 | Blocker | expo export --platform web -> static site. Your kickoff insurance.
9 | P1 Data spine | Schema v1 migration: profiles, players, teams, cards, card_instances, packs, gems_ledger, stat_lines | 2026-08-20 | 2026-08-22 | 3 | Not started | 4 | Blocker | card = player template. card_instance = the copy a user owns. Never merge.
10 | P1 Data spine | RLS policies + a test that proves user A cannot read user B's roster | 2026-08-22 | 2026-08-22 | 1 | Not started | 9 | Blocker | Write the failing test first. Your testers are engineers.
11 | P1 Data spine | StatsProvider interface + balldontlie adapter | 2026-08-21 | 2026-08-22 | 2 | Not started | 2 | Blocker | Nothing above this layer imports balldontlie types.
12 | P1 Data spine | Nightly players/teams sync Edge Function + cron | 2026-08-23 | 2026-08-23 | 1 | Not started | 11 | 4 | Team rosters only exist from the 2025 season onward.
13 | P1 Data spine | Weekly DFS salary snapshot -> rarity band assignment | 2026-08-23 | 2026-08-24 | 2 | Not started | 11, 12 | 3 | Persist every snapshot - slates disappear. Fall back to 2025 season stats.
14 | P1 Data spine | Stat ingestion: games -> game_ids -> /stats paginated -> raw stat_lines | 2026-08-24 | 2026-08-25 | 2 | Not started | 11 | Blocker | /stats has no week param and no fantasy points. Resolve /games -> ids first.
15 | P1 Data spine | Scoring engine: pure fn(stat_line, rules_version) -> points, with unit tests | 2026-08-25 | 2026-08-25 | 1 | Not started | 14 | Blocker | Store raw stats AND points. Scoring will change; recompute, never re-ingest.
16 | P1 Data spine | VALIDATE ingestion against live preseason games | 2026-08-26 | 2026-08-28 | 3 | Not started | 14, 15 | Blocker | HARD DEADLINE. Preseason ends ~Aug 29; then no live data until Sept 9.
17 | P2 Core loop | Card component: rarity-driven palette, position glyph, team as 3-letter text | 2026-08-25 | 2026-08-26 | 2 | Not started | 9 | 2 | No logos, jerseys, or photos. Palette keyed to rarity, not team.
18 | P2 Core loop | Server-side pack opening: Postgres RPC, weighted RNG, transactional gem debit | 2026-08-26 | 2026-08-27 | 2 | Not started | 9, 13 | Blocker | RNG and gem math never leave the server. Assume Charles Proxy.
19 | P2 Core loop | Pack open UI + reveal animation (reanimated, works on web + iOS) | 2026-08-27 | 2026-08-29 | 3 | Not started | 17, 18 | 1 | First thing to downgrade. A static reveal still works.
20 | P2 Core loop | Collection screen: grid, filter by position/rarity, card detail | 2026-08-28 | 2026-08-29 | 2 | Not started | 17 | 3 | Virtualize the list now, not later.
21 | P2 Core loop | Lineup builder + server-enforced weekly lock | 2026-08-29 | 2026-08-31 | 3 | Not started | 9, 20 | Blocker | Lock time computed server-side. Never trust a client clock.
22 | P2 Core loop | Gem faucet v1: weekly grant + earn from weekly score | 2026-08-30 | 2026-08-31 | 2 | Not started | 18 | 4 | Weekly grant only here. Start stingy - you can always grant more.
23 | P3 Score+Board | Live scoring job: 5-min cron on gamedays -> weekly_scores | 2026-08-31 | 2026-09-01 | 2 | Not started | 15, 21 | Blocker | 10 calls per sweep vs a 600/min ceiling. Do not over-engineer caching.
24 | P3 Score+Board | Global leaderboard view + screen | 2026-09-01 | 2026-09-02 | 2 | Not started | 23 | 2 | One global board. No leagues or friend lists in the beta.
25 | P3 Score+Board | Injury-status warning on the lineup screen | 2026-09-02 | 2026-09-02 | 1 | Not started | 12 | 1 | Cheap win - the injuries endpoint is already in your tier.
26 | P3 Score+Board | Push notifications: lineup lock reminder + weekly results | 2026-09-02 | 2026-09-02 | 1 | Not started | 7, 23 | 1 | FIRST THING CUT. iOS only anyway.
27 | P4 Ship | Privacy policy page + support URL + App Privacy questionnaire | 2026-09-01 | 2026-09-01 | 1 | Not started | 8 | Blocker | Blocks submission. Everyone forgets this and loses a day.
28 | P4 Ship | Internal TestFlight build to friends (up to 100, NO review) | 2026-09-01 | 2026-09-01 | 1 | Not started | 7, 21 | Blocker | Each tester needs an App Store Connect role. Invite them now.
29 | P4 Ship | FEATURE FREEZE | 2026-09-02 | 2026-09-02 | 1 | Not started | 22, 24 | Blocker | Bugs only after this line.
30 | P4 Ship | Submit external TestFlight for Beta App Review | 2026-09-02 | 2026-09-02 | 1 | Not started | 27, 29 | Blocker | 1-2 days typical. This date budgets one rejection round.
31 | P4 Ship | Abuse pass: try to grant yourself gems and set a lineup post-lock | 2026-09-03 | 2026-09-03 | 1 | Not started | 18, 21, 22 | Blocker | Attack your own API with curl. If you can do it, they will.
32 | P4 Ship | Bug fix buffer | 2026-09-03 | 2026-09-08 | 6 | Not started | 29 | Buffer | Six days. It will not feel like enough. It never does.
33 | P4 Ship | Friends dry run: simulated Week 0 end-to-end | 2026-09-05 | 2026-09-06 | 2 | Not started | 28 | Blocker | Full loop: pack -> lineup -> lock -> score -> board. Fake stats if needed.
34 | P4 Ship | Set up EAS Update (OTA) channel | 2026-09-04 | 2026-09-04 | 1 | Not started | 30 | 2 | Push JS fixes mid-beta without another App Review. Worth the hour.
35 | P5 Kickoff | Week 1 opener - monitor ingestion live | 2026-09-09 | 2026-09-09 | 1 | Not started | 33 | - | Wednesday opener (Thursday game is in Australia). Watch the first sweep.

## Milestones
Milestones & Progress
PROGRESS
Total tasks | 35
Done | 0
In progress | 0
Blocked | 0
Not started | 35
Cut | 0
% complete | 0%
Blockers left | 23
Days to kickoff | 22
MILESTONES
Date | Milestone | Why it matters | Hit?
2026-08-21 | Dev build on your phone + web deployed | If this slips, everything slips. | No
2026-08-25 | Ingestion produces real fantasy points from real games | The moment the app has a reason to exist. | No
2026-08-29 | Preseason validation complete | HARD DEADLINE - last live data before Week 1. | No
2026-08-31 | Core loop playable end to end | Open pack -> collection -> lineup -> lock. | No
2026-09-01 | Internal TestFlight in friends' hands | No App Review needed. Real users, 8 days early. | No
2026-09-02 | Feature freeze + external TestFlight submitted | Budgets one rejection round. | No
2026-09-06 | Friends dry run complete | Simulated Week 0, full loop. | No
2026-09-09 | KICKOFF - NFL Week 1 opener | Wednesday. 22 days from Aug 18. | No

## Deferred
Explicitly NOT in the Sept 9 beta
A contract with yourself. Anything that creeps back in costs the kickoff date.
Feature | Target | Why it waits
Sets / Museum | Ship Week 3 | Nobody can complete a set in Week 1 anyway. Buys three weeks.
Card selling | Late Sept | Blocked on the set-reward decision. Gem sinks balance together.
Tier ranking (museum duplicates as fuel) | Late Sept | Makes duplicate pulls valuable. Not day-one important.
Free agent market | October | Adds an economy AND a moderation surface.
Discord bot (read-only) | October | Lock + pull results to a channel, OAuth-linked. A weekend once core is stable.
In-app purchases | Not in beta | Earned gems only. Tests fun before monetization.
Profile beyond name + avatar | Late Sept | No bios, stats pages, or follower graph.
Real player art | When you generate it | Position glyph + rarity palette. Layout does not change when art lands.

## Risks
Risks & Mitigations
Risk | Likelihood | Impact if it lands | Mitigation
Apple Developer enrollment stalls | High | Nothing reaches a phone | Started Aug 18. Web build ships regardless.
Beta App Review rejects the external build | Medium | Friends cannot install by Sept 9 | Web live Aug 21 + internal TestFlight covers 100 friends without review.
Preseason data window closes ~Aug 29 | High | Ingestion untested against live data until kickoff | Task 16 is hard, not soft. If it slips, replay 2025 stat lines.
No DFS slates in preseason / bye weeks | Medium | Rarity assignment has gaps | Fallback tier from 2025 season stats. Persist every snapshot.
Scoring rules change mid-beta | Certain | Rescoring pain | Raw stat_lines stored apart from points, rules versioned. Recompute is a query.
balldontlie /stats has no week param | Certain | Naive ingestion is wrong | Resolve week -> game_ids via /games. Handled in task 14.
Undocumented API shape drift | Low | Ingestion breaks silently | StatsProvider (task 11) makes a swap one file. Alert on zero-row sweeps.
Scope creep from your own good ideas | Certain | Miss kickoff | The Deferred tab is the contract. Sept 2 freeze enforces it.

## Decisions
Locked decisions & open questions
Decision | Status | Rationale / what unblocks it
Expo Router universal app (one codebase -> iOS + web) | LOCKED | One codebase, file-based routing, native on iOS and React Native Web in the browser. A separate Next.js app is the trap on a first universal build.
Supabase for auth, Postgres, Edge Functions, cron | LOCKED | Already wired up. RLS does the multi-tenant work for you.
balldontlie NFL GOAT, $39.99/mo, 600 req/min | LOCKED | A supported contract, not Sleeper's undocumented endpoints. Adds DFS salaries, injuries, play-by-play.
Rarity derived from DFS salary bands | PROPOSED | Salary is a weekly market valuation of every player: rarity with zero manual curation, and gated set slots become a query.
Server-authoritative RNG, gems, and lineup locks | LOCKED | Testers are your engineer friends. Assume Charles Proxy.
No player photos, logos, or jerseys | LOCKED | Names + stats have solid fantasy precedent. Likenesses and marks do not.
Zero IAP in the beta | LOCKED | Sidesteps loot-box odds disclosure, StoreKit, and the 30%.
Set reward mechanic (gated slots vs points-scaled payout vs duplicate fuel) | OPEN | Blocks card schema and faucet rates, both painful to change once people own collections. Decide before task 9 ships Aug 22.
Fantasy scoring rules (PPR? bonuses? tier multipliers?) | OPEN | Needed by task 15. Low stakes - raw stats are stored, rescoring is a query.